## Guidance (hidden)
Risks - Issues - Lessons Learnt Templates Guidance
| Risk register | Issue log | Lessons learnt log
Purpose | To assist you in managing risks, i.e. reduce the likelihood of risks becoming issues or to lower their impact on the project if they do occur. | To assist you in managing issues, i.e. prioritise and monitor issues and their action plans. Issues are risks which have occurred. They may have been logged in the risk register or may not have been foreseen before they happened. | To ensure that the PMO do not repeat the same mistakes twice, and can repeat successes throughout the programme. To provide a basis for the programme closedown report.
Benefits to PMO | Completing, updating, and circulating the risk register regularly should help avoid forseeable risks from having a large negative impact on the programme's outcomes. It provides you with a record of risks which have been identified and the actions taken to treat them. | Gives you confidence that identified issues are being resolved appropriately. It provides you with a record of issues that have been idenitified and who is responsible for resolving them. | Ensures that the PMO are well informed as to what has gone well and what has not gone so well during the project. Increases likelihood of project success as PMO are aware of what does and does not work in the project environment.
Creation | To be created at scoping stage. Initial risks are best identified as part of a workshop attended by partners during approval stage. | To be created at scoping stage. Issues may be raised at any stage of the project by any project partner. | To be created at scoping stage. Lessons learnt may be flagged at any stage of the programme by any project partner.
Circulation | Should be circulated to Project Team for review at every project team meeting. Key risks (those which are 'high-high, high-medium, or medium-high), their due dates and their action plans should be raised at the Programme Board. | Critical' and 'overdue' issues should be flagged to the Programme Board. | Should be circulated to Project Board for review at every meeting to raise awareness about best practice.
Review & update | Should be reviewed and (if necessary) updated immediately prior to every progress report, and also if project scope, project plan or business case change. When reviewing, you should examine each risk to see if it has increased, decreased, disppeared, happened or stayed the same. Risk owners should be contacted to gain their input. Risk owners may state the risk has happened, in which case it should be logged in the issue log. | Should be reviewed and (if necessary) updated immediately prior to every progress report, and also if project scope, project plan or business case change. Contact Issue Owner to see whether they have completed the action plan, the issue has been resolved, or its due date has been moved due a to a change in circumstance. | Should be updated whenever you encounter an issue or a partner informs you of a lesson learnt.

## Risk matrix
Risk Matrix
The following matrix is used to calculate a risk's rating:
Likelihood
|  | AMBER | RED | RED
High
|  | GREEN | AMBER | RED
Medium
|  | GREEN | GREEN | AMBER
Low
Impact
|  | Low | Medium | High
Threat Levels
These are used to determine the timing of a risk.
Present | The risk is already present and is likely to continue until mitigated or accepted
Imminent | The risk will occur within the next three months
Close | The risk will occur within the next twelve months
Remote | The risk will occur within the lifetime of the programme

## Risk register
Risk Register
Programme Name: |  |  |  |  | Sharing Cities (H2020 Lighthouse) |  |  |  |  | Last updated: | 10th February 2016 - Sandeep Duggal
Programme Manager: |  |  |  |  | Sandeep Duggal
Nb/ all 'High / High', 'Medium / High', or 'High / Medium' risks must be reported to the Programme Board
1 |  |  |  | 2 |  | 3 |  |  |  | 4 |  | 5
Risk # | Work Package | Date Raised | Work Package Lead | Risk description |  | Assessment |  |  |  | Proposed risk-mitigation measures |  | Post-Mitigation Assessment |  |  | Risk owner | Tasks Raised on Task Log (if any)? | Date of last review | Direction of Travel | Status |  | Date Closed
[6 empty] | Threat Level | Likeli-hood | Impact | Rating |  |  | Likeli-hood | Impact | Rating
R1 | 1 | 2016-01-01 | Andrew Collinge | Partner is unable to remain committed to the Programme result in partner withdrawal. |  | Present | Low | High | Amber | 1. Continuous monitoring of partners’ progress and engagement in the project. 2. If critical expertise or capacities lack in existing partner, discuss with INEA the possibility of finding a new partner or subcontracting a specific set of activities. 3. Establishment of a continuous two way stakeholder engagement. |  | Low | High | Amber | PMO |  | 2016-02-10 | On Target | Open
R2 | 1 | 2016-01-01 | Andrew Collinge | Partner underperforms |  | Present | Low | Medium | Green | 1. The project and city coordinators will track the progress and delivery of each of the deliverables against overall project and city-specific project plans. Where partner performance is of concern, the City Leads will first liaise with the relevant WP and/or Task Leader to ensure that appropriate corrective measures are taken and suggest contingency plans. The City Leads will also promptly inform the PMO and consult on the actions to be taken. 2. Although the City Leads are responsible to manage the risk/issue, the Programme Board will act as the ultimate decision making body for solving disputes and proposing/validating corrective actions. If the risk becomes an issue, a sub-commitee will be formed. |  | Medium | Medium | Amber | PMO |  | 2016-02-10 | Worse | Open
R3 | 1 | 2016-01-01 | Andrew Collinge | Loss of knowledge, expertise due to key staff changes. |  | Present | Medium | Medium | Amber | 1. Re-allocation of the person’s responsibilities to another person (preferably from the same partner, except if field of expertise is then extinct). 2. Implementation of standard induction tools. Comprehensive handover process. 3. Liquid Planner supports task reallocation. |  | Medium | High | Red | PMO |  | 2016-02-10 | Worse | Open
R4 | 1 | 2016-01-01 | Andrew Collinge | Partners do not reach consensus on a certain decision |  | Present | Low | Medium | Green | 1. A clear governance structure has been established with the Programme Board being the ultimate decision making body. |  | Medium | High | Red | PMO |  | 2016-02-10 | Worse | Open
R5 | 1 | 2016-01-01 | Andrew Collinge | Activity/sub-activity takes longer than expected. |  | Present | Low | Medium | Green | 1. Programme management from PMO. 2.Close monitoring of the activities development and planning. 3. Study the possibility of extension of the duration of the task (in the event of an unexpected degree of complexity of the task). 4. Re-evaluate the scope of the activity/sub-activity in order to assess whether non critical tasks can be lighten up. |  | High | Low | Amber | PMO |  | 2016-02-10 | Worse | Open
R6 | 1 | 2016-01-01 | Andrew Collinge | Procurement process takes longer than expected. |  | Imminent | Medium | Medium | Amber | 1. Identify potential experts as soon as INEA announces the project is going into the negotiation phase 2. Start the procurement process as soon as the Grant Agreement is signed |  |  |  |  | PMO |  |  |  | Closed |  | 2016-01-01
R7 | 3 | 2016-01-21 | Francisco Goncalves | Delays in delivery of project hardware. |  | Close | Medium | Medium | Amber | 1. Delay will be flagged early at a local City Board and the project coordinator will be notified. The local coordinator (as led by the City Board) will be responsible for looking for solutions, working with local stakeholders) 2. look for similar opportunities within the city which can provide an equivalent data stream 3. If this cannot be identified, the consortium will discuss with the project officer whether a reallocation of budgets to an equivalent task is appropriate and/or a reconfiguration of the project to not rely on a given piece of hardware. |  | Medium | Medium | Amber | PMO |  | 2016-02-10 | On Target | Open
R8 | 3 | 2016-01-21 | Francisco Goncalves | Failures at the interface between open data platforms and energy hardware. |  | Close | Medium | High | Red | 1. a complete set of data protocols to be used on the project will be provided to the involved partners, which will ensure controls systems and data gathering equipment is compatible with the data platform. 2. City Leads will coordinate the work between data platform operators and infrastructure system provider to ensure a successful resolution is reached. |  | Low | High | Amber | PMO |  | 2016-01-10 | Better | Open
R9 | 1 | 2016-02-10 | Andrew Collinge | Outcomes, goals and deliverables are not delivered. |  | Imminent | Low | High | Amber | 1. Continuous quality control mechanisms 2. Adjust activities or create contingency activities to deal with the new circumstances 3. If impact is critical, decisions are taken by the Programme Board. |  |  |  |  | PMO |  |  |  | Open | Open
R10 | 4 | 2016-01-21 | Jason Warwick | Delays in implementation of the Urban Sharing Platforms. |  | Remote | Low | High | Amber | 1. Close alignment of WP4 with WP3. 2. Alignment of WP4 with WP2. 3. Managed through City Boards. |  | Low | High | Amber | PMO |  | 2016-02-10 | On Target | Open | Closed
R11 | 4 | 2016-01-21 | Jason Warwick | Data compatibility within open platforms, both within and between cities. |  | Close | Medium | Medium | Amber | 1. significant attention to data protocols and specific tasks (which ones?) are established to ensure all partners are clear on the data requirements at the start of the project. |  | Medium | Medium | Amber | PMO |  | 2016-02-10 | On Target | Open
R12 | 4 | 2016-01-21 | Jason Warwick | Regulatory/privacy issues preventing use of citizen data as planned. |  | Close | Low | Medium | Green | 1. The Project will look to work with regulators to challenge existing regulations and propose new solutions which respect privacy whilst still allowing the benefits of the city wide data architecture to be achieved. 2. Modify the planned activity to comply with the regulations, which may simply lead to a less effective control or engagement process, but would not impact the overall project objectives. |  | Low | Medium | Green | Jason Warwick |  | 2016-02-10 | On Target | Open | High
R13 | 1 | 2016-01-01 | Andrew Collinge | Partner does not validate deliverables |  | Close | Low | Medium | Green | 1. Ensure strong engagement of partners and involvement in all activities of the project. 2. Validate intermediate steps of the elaboration of the deliverables. 3. Assess whether partner conditionings to the validation can be accommodated. |  | Low | High | Amber | PMO |  | 2016-02-10 | Worse | Open | Medium
R14 | 2 | 2016-01-01 | Claire Mookajee | Absence of citizen buy-in |  | Close | Low | High | Amber | 1. Continuous monitoring of citizen participation. 2. Partners will experiment with a series of incentives to encourage take up ranging from competitions, prizes (linked to e.g. local shops, or even across the smart cities in the project), local advertising campaigns, television and radio slots to promote the project and public campaigns aimed at ensuring friendly competition between communities. |  | Medium | High | Amber | PMO |  | 2016-02-10 | Worse | Open | Low
R15 | 5 | 2016-01-01 | Nathalie Guri | Low acceptance of the outputs of the project by third parties not involved in the project |  | Remote | Low | High | Amber | 1. Thorough stakeholders analysis to compose the Advisory Board and national stakeholders groups. 2. Strong communication and dissemination strategy. 3. Reinforce communication strategy targeted at the identified group. |  | Low | High | Amber | PMO |  | 2016-02-10 | On Target | Open
R16 | 1 | 2016-01-21 | Andrew Collinge | Business Continuity in the event of City Hall being unavailable for occupation or there is a sustained interruption of ICT services to the building or a significant percentage of staff are abstracted from the business. |  | Present | Low | Medium | Green | The GLA has a Corporate Business Continuity Plan (BCP), sets out the framework under which the Greater London Authority will operate in a business continuity situation. This plan has been replicated at a directorate level which have developed their own business continuity processes and plans which aim to reduce the impact of any significant event. |  | Low | Medium | Green | PMO |  | 2016-02-10 | On Target | Open
R17 | 3 | 2016-01-21 | Francisco Goncalves | WP3 tasks do not deliver forseen results. |  | Imminent | Low | High | Amber | 1. Continuous quality control mechanisms from Work Package Leads. 2. Adjust activities or create contingency activities to deal with the new circumstances. 3. If impact is critical, decisions are taken by the Programme Board. |  | Low | High | Amber | PMO |  | 2016-02-10 | On Target | Open
R18 | 3 | 2016-01-21 | Francisco Goncalves | Low acceptance of the outputs of WP3 by third parties not involved in the project. |  | Imminent | Low | Low | Green | 1. Align with WP2 & WP6. |  | Low | Low | Green | Francisco Goncalves |  | 2016-02-10 | On Target | Open
R19 | 4 | 2016-01-21 | Jason Warwick | WP4 results can be achieved only if aligned with the plans & tasks in WP2 & WP3. Part of the work contributing to the overall USP architecture is actually included in other WPs (e.g., implementation of sensing layer, end-user apps). |  | Present | Low | High | Amber | 1. Ensure that proper coordination and decision mechanisms between WPs are in place. 2. All partners should be on the same page, i.e., share the “big picture” of the USP reference model, its “boundaries”, and how its implementation takes place in the different WPs. |  | Low | High | Amber | PMO |  | 2016-02-10 | On Target | Open
R20 | 4 | 2016-01-21 | Jason Warwick | Licenses or other IP related issues prevent partners from actually sharing their solutions with other partners. |  | Remote | Low | High | Amber | 1. Ensure that proper licensing and sharing schemes are in place from the outset. 2. Check technical feasibility. 3. Use goverance arrangments to resolve any issues. |  | Low | High | Amber | PMO |  | 2016-02-10 | On Target | Open
R21 | 4 | 2016-01-21 | Jason Warwick | The 3 core cities are inconsistent in terms of look, feel, value and or content. |  | Remote | Low | Medium | Green |  |  | Low | Medium | Green |  |  |  |  | Open
R22 | 5 | 2016-01-21 | Bernadett | Replication not considered as a priority by lighthouse cities. |  | Present | Medium | High | Red | Explain the importance of replication to lighthouse cities as well as to the entire consortium and explain how cruicial it is for the success of our project. Explain to lighthouse cities what they can get out of this WP. |  | Medium | Low | Green | Bernadett |  |  |  | Open
R23 | 5 | 2016-01-21 | Bernadett | Difficulties in pairing up lighthouse and follower cities. |  | Present | Low | Medium | Green | Identify areas of interest, common points, similar challenges in lighthouse and follower cities. |  | Medium | Low | Green | Bernadett |  |  |  | Open
R24 | 5 | 2016-01-21 | Bernadett | Difficulties in engaging cities outside the consortium |  | Present | Medium | Medium | Amber | Lighthouse and follower cities to activate their own networks. EUROCITIES to use its structure/membership to attract cities outside the consortium |  | Medium | Low | Green | EUROCITIES |  |  |  | Open
R25 | 6 | 2016-01-21 | Natalie | Communication not ocnsidered a priority by consortium partners. |  | Present | Low | High | Amber | Explain the importance of communication and dissemination activities to the entire consortium and explain how crucial it is for the success of our project. |  | Low | Low | Green | Natalie Guri |  |  |  | Open
R26 | 6 | 2016-01-21 | Natalie | Multiple participation/uncoordinated participation of the partners in smart cities events. |  | Close | Low | Low | Green | EUROCITIES to establish good monitoring and planning tools. All partners to communicate about their participation in events. |  | Low | Low | Green | EUROCITIES |  |  |  | Open
R27 | 6 | 2016-01-21 | Natalie | Difficulties to attract the attention of various stakeholders as we are 1 out of at least 7 SCC lighthouse projects. |  | Imminent | Low | Medium | Green | Work together to explain our USP (see links with WP4). Be very visible at local/national/European/International events/media. |  | Low | Low | Green | Natalie Guri |  |  |  | Open
R28 | 7 | 2016-01-21 | Graham Colclough | WP Resource balance does not match planned activity |  | Present | Medium | High | Red | 1. Review Plan milestones and deliverables. 2. Reforecast resource requirements. 3. Resolve through Programme Board. |  | Low | Low | Green |  |  |  |  | Open
R29 | 7 | 2016-01-21 | Graham Colclough | Internal Alignment - Proactive content proviision from WP 2,3, 4. |  | Close | Low | High | Amber | Identify content from WP2, 3, 4 forward look calendar and timetable requests. Discuss opportunities on regular basis with WP leads. |  | Low | Low | Green |  |  |  |  | Open
R30 | 7 | 2016-01-21 | Graham Colclough | External Alignment - Success of Communications and replication. (WP 5&6) |  | Close | Medium | Medium | Amber | Identify content from WP5 and 6 forward look calendar and timetable requests. Discuss opportunities on regular basis with WP leads. |  | High | High | Green |  |  |  |  | Open
R31 | 7 | 2016-01-21 | Graham Colclough | WP doesn't produce new business models/outcomes |  | Remote | Medium | High | Red | 1. Develop Benefit Realisation Plan. 2. Create ten Practical Common Solutions. |  | Low | Medium | Green |  |  |  |  | Open
R32 | 7 | 2016-01-21 | Graham Colclough | Design Approach - Ease-of-Replication/Aggregation |  | Imminent | Low | Medium | Green | "How to" Guides |  | Low | Low | Green |  |  |  |  | Open
R33 | 7 | 2016-01-21 | Graham Colclough | Availability of Funds/cashflow |  | Present | Low | High | Amber |  |  | High | High | Green |  |  |  |  | Open
R34 | 7 | 2016-01-21 | Graham Colclough | Alignment with EIP_SCC; H2020 projects; EIB/Regio; 6-N |  | Imminent | Medium | Medium | Amber |  |  | High | High | Green |  |  |  |  | Open
R35 | 8 | 2016-01-21 | John Polak | Adequate baseline data are not available for one or more cities. |  | Close | Medium | High | Red | Collect new Baseline data (PMO comment = Cost element??) |  | Low | Medium | Green |  |  |  |  | Open
R36 | 8 | 2016-01-21 | John Polak | Baseline and/or monitoring data prove to be of poor quality. |  | Close | High | High | Red | Appraise existing baseline data and rigorously pilot new data collection methodologies. |  | Low | Medium | Green |  |  |  |  | Open
R37 | 8 | 2016-01-21 | John Polak | Inadequate capacity or funds to collect suitable data. |  | Imminent | High | High | Red | Increase data budget (PMO comment = shouldn't this have already been costed?If so, Likelihood can be downgraded) |  | Medium | Medium | Amber |  |  |  |  | Open
R38 | 8 | 2016-01-21 | John Polak | Commercial supply chain refuse to provide necessary data. |  | Close | Medium | Medium | Amber | Ensure contracts require data to be provided. |  | Low | Low | Green |  |  |  |  | Open
R39 | 8 | 2016-01-21 | John Polak | Plans for the implementation of the PPP measures remain volatile delaying the design of monitoring. |  | Close | High | High | Red | Manage (PMO - ???) |  | High | High | Red |  |  |  |  | Open
R40 | 8 | 2016-01-21 | John Polak | Some PPP measures are not implemented. |  | Imminent | High | Medium | Red | Identify problems early and cut funding before good money follows bad. |  | High | Medium | Red |  |  |  |  | Open
R41 | 8 | 2016-01-21 | John Polak | Travel budget not sufficient to enable adequate coordination. |  | Imminent | High | High | Red | Increase the travel budget (PMO - costed??) |  | High | High | Red |  |  |  |  | Open
R42 | 8 | 2016-01-21 | John Polak | CMEF and agreed protocols, etc. are not properly or fully-implemented in all cities. |  | Close | Medium | High | Red | Strong WP management and coordination. (PMO - details?) |  | Medium | Medium | Amber |  |  |  |  | Open
R43 | 8 | 2016-01-21 | John Polak | Insufficient commitment from city authorities to sustain activities for 5 yrs. |  | Present | Medium | Medium | Amber | Pay appropriate attention to internal political ocmmunications (PMO - needs more detail, insufficient) |  | Medium | Medium | Amber |  |  |  |  | Open
R44 | 8 | 2016-01-21 | John Polak | Reluctance to admit and learn from failure (the M&E will inevitably show that not everything worked as planned or had the anticipated desired effects). |  | Present | High | Medium | Red | Inculcate culture of rigour and transparency |  | Low | Low | Green |  |  |  |  | Open
Note on E6: Describe the risk in enough detail that someone who is not working on the project can understand it. Risks should be logged in the format 'There is a risk that (…state what could occur), which means that (...state the potential impact that the risk is likely to have). E.g. There is a risk that the software developer will not deliver in time, which means that the 'go live' date will have to be pushed back
Note on K6: If you choose to put in place multiple responses to a risk, use the 'Alt+Rtn' keys to get multiple lines within the same cell
Note on M6: This is the RAG rating of the effects of the mitigation. Does the mitigation reduce the risk?
Note on G7: This is the timescale of the risk. See Risk Matrix
Note on H7: Select from the list below how likely it is that the risk will occur
Note on I7: Select from the list below what level of impact the risk is likely to have if it does occur
Note on J7: Use the risk matrix on the preceding tab to work out the risk rating
Note on M7: Select from the list below how likely it is that the risk will occur
Note on N7: Select from the list below what level of impact the risk is likely to have if it does occur
Note on O7: Use the risk matrix on the preceding tab to work out the risk rating

## Issues log
Issues Log
|  |  | Programme Name | Sharing Cities (H2020 Lighthouse) |  | Last updated: | 2016-01-14
|  |  | Programme Manager: | Sandeep Duggal |  | Critical | Issue needs resolving immediately - already impacted on project/programme plan.
[6 empty] | Overdue | Issue needs resolving ASAP - will adversely impact on project/programme plan if not resolved before next progress report.
Nb/ all 'overdue' and 'critical' issues must be reported to the Programme Board. | [5 empty] | OK | Issue needs resolving but is not presently blocking progress.
Issue # | Work Package | Work Package Lead | Date issue was raised | Issue description | Potential impact | Action plan |  | Issue owner | Status
I-1 | 1 | Andrew Collinge | 2016-01-14 | Responses to the request for comments on Consortium Agreement were delayed. Attachment 1 on Background has still not been received from many partners. | Some partners may not be able to accede to the Agreement without the Consortium Agreement in place. Delays with acceeding to the Grant Agreement will delay payments to partners and potentially jeopardise the programme. | Comments received so far have been passed to GLA Legal. No further comments can be accepted. Partners will be encouraged to sign the Grant Agreement by 20th January to avoid payment delays. Note that it is not a Commission requirement that partners sign the Consortium Agreement before the Grant Agreement. |  | PMO | Critical
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
I-11
I-12
I-13
I-14
I-15
I-16
I-17
I-18
I-19
I-20
I-21
I-22
I-23
I-24
I-25
I-26
I-27
I-28
I-29
I-30
I-31
I-32
I-33
I-34
I-35
I-36
I-37
I-38
I-39
I-40
I-41
I-42
I-43
I-44
Note on E9: Describe the issue in enough detail that someone who is not working on the project can understand it, e.g. 'Software developer is ill - not expected to return to work for a week'
Note on F9: State what impact the issue will have if not resolved, e.g. Critical task - will put back 'go live' date by a week.
Note on G9: State the action(s) which have been agreed to resolve the issue
Note on I9: Agree who should 'own' the task, this should be the person who is best placed to see it through to resolution, that is, the person who: a) is responsible for this area of work, or b) will be most adversly affected if the issue is not resolved, or c) has the time and the right skills to resolve the issue
Note on J9: Select a status from the drop down - key to statuses above

## Lessons learnt log
Lessons Learnt Log
Programme name: | Sharing Cities (H2020 Lighthouse) | Last updated: | 2016-02-10
Programme Manager: | Sandep Duggal
Project stage | Lesson | Positive / negative | How to replicate (positive lessons) / avoid (negative lessons) | Raised by / further questions to
Set Up | Follower Cities did not feel adequately included in the shaping of the programme. | Positive | Early engagament with follower cities in programme design. | Antony Page

## List (hidden)
Work Package | Open | Set Up | Positive | Present | Low | Green | Better
1 | Issue | Delivery | Negative | Imminent | Medium | Amber | On Target
2 | Closed | Closure |  | Close | High | Red | Worse
3 |  |  |  | Remote |  |  | No Data
4
5
6
7
8